## Sheet1
ID | Title | State | Assigned To | Story Points | Sprint | Duration | Comments
17666 | Kanban screen to automatically refresh, showing changes made by other users | Closed | Raja Dashnamoorthy | 5 | 64 | Jan 18 to Feb 1 | 1. 32 story points completed. 2. only two days wokred in this User story. 3. apart from this there are two other user stories 11 storypoints are carried from her to next both are completed and ready for merging but doesn’t make the cutt off. 4. sum off 85.75 user stories are completed / worked from sprint 61 to 63 which is an average of 29.25 story points which is along with Smart factory.
18648 | User option to pin the search bar open for a given queue | Closed | Raja Dashnamoorthy | 8 | 64
17324 | Date reference handling in the V5 store UI - DATEVISIBLE, DATECLEAR, NAME | Closed | Raja Dashnamoorthy | 10 | 64
17326 | Store Documents CLEARGRIDAFTERUPDATE | Closed | Raja Dashnamoorthy | 1 | 64
18270 | (Bug Fix) Document to store - deployment browser cache bug | Closed | Raja Dashnamoorthy | 8 | 64
17665 | Job counts in Kanban column header | Closed | Raja Dashnamoorthy | 2 | 63 | Dec 28 - Jan 14 | 1.26.5 story points completed. 2. No leave taken.
18647 | Refresh Kanban after drag operation is completed | Closed | Raja Dashnamoorthy | 0 | 63
18649 | Add 3rd icon slot to Kanban card (middle) | Closed | Raja Dashnamoorthy | 3 | 63
17663 | Colour border around each Kanban card | Closed | Raja Dashnamoorthy | 3 | 63
18152 | Convert purple Kanban toastr warnings to amber style (consistent with general application warnings) | Closed | Raja Dashnamoorthy | 1 | 63
17662 | Tooltips on kanban card icons | Closed | Raja Dashnamoorthy | 3 | 63
18513 | Misleading error message when entering Alpha into numeric fields | Closed | Raja Dashnamoorthy | 8 | 63
17785 | (Bug fix) Page numbers on store page get refreshed on add to existing page and redirect | Closed | Raja Dashnamoorthy | 3 | 63
17690 | Columns in the Add To Existing list (add date and pages) | Closed | Raja Dashnamoorthy | 3 | 63
18662 | Housekeeping-Enable Swagger in test environment | Closed | Raja Dashnamoorthy | 0.5 | 63
18590 | 18225: No separation between indexing modes and Add To Existing / additional options | Closed | Raja Dashnamoorthy | 1 | 62 | Dec 10 - 24 | 1. 3 story points completed, 2. 1 day leave on Dec 13. 3. Invloved in the Design and analysis , UX design approval of next sprint user stories and also worked few of the user stories and carried to the next sprint. 4. Involved in Smart factory Intial code, Smart factory Dynamic data base table design, worked with Clients to get approval on the Database design, Worked with Development team, and gave them knowledge of the code and database tables. started working on the Workflow Architecure. 5. Daily get it to touch with sowmiya and helped in her interview preparation.
18221 | (Bug fix) Page indexing mode changes after indexing - should retain the last used indexing mode | Closed | Raja Dashnamoorthy | 2 | 62
18390 | Raja - review and use Error/warning notifications WIKI | Closed | Raja Dashnamoorthy | 0.25 | 61 | Nov 24 to Dec 8 | 1. 13.25 story points completed. 2. No Leave taken. 3. Started working with Smart factory attended KT session, wokred with Team Syed and Sagar about the code set up and other plans. 4. Worked with Frank and Alex in getting Accesses , creating pipelines and repositories. 5. Worked on the User story 6422 after fixing it during the code review Andrew has found that we need to use a different approach to implement it. so it doesnt completed and carried over to next sprint. which is 3 story point inititialy currently 10 story point big. and it is completed in sprint 64 but doesnt make the code cuttoff. 6. 18063 User story is initially 3 story point during testing we found that Matt is completed those chanhes as part of another user story. so they chnaged the story points and closed the US. 7. 18270 is the challeging bug , i spent more time on this , even it takes three days to replicate it. after i fixed we found serious of bugs. so we dicussed and decided to follow a different approch so 18651 and 18652 user stories created to implement the new user story and this user is 8 story points and closed as part of sprint 64. so effort is nearly 5 + 2 + 8 + 13.25 almost 28 story points
18393 | Document lock time-out can occur whilst user is still active (pressing keys) - silently extend document lock | Closed | Raja Dashnamoorthy | 3 | 61
18469 | Should not show "Document cannot be split" for single page documents | Closed | Raja Dashnamoorthy | 1 | 61
18476 | Slow response to Store button click | Closed | Raja Dashnamoorthy | 5 | 61
18514 | Format of upload message is messy | Closed | Raja Dashnamoorthy | 3 | 61
18063 | Store Documents layout issues at small window sizing (Tablet/Small Screen Styling Changes) | Closed | Raja Dashnamoorthy | 1 | 61
18031 | (Bug Fix) Drop down lists in Store Documents to appear on top of image area | Closed | Raja Dashnamoorthy | 3 | 60 | November 8- 22 | 1. 8 Story points completed. 2. in this sprint I have worked on the Novatiq issue. 3. Smart factory kickstart happened. 4. Nov 10, 11, 12 and 18 4 days I took leave.
18272 | (Bug Fix) Cannot use drop-downs in Firefox browser | Closed | Raja Dashnamoorthy | 3 | 60
18231 | Bug fix - Warning message if date is blank is messy | Closed | Raja Dashnamoorthy | 1 | 60
18361 | Bug fix - Document date value is not reset between documents | Closed | Raja Dashnamoorthy | 1 | 60
17680 | Stop controls moving up and down on the store documents page | Closed | Raja Dashnamoorthy | 8 | 59 | Oct 21 - November 4 | 1. 31 story points completed. 2. No Leave taken. 3. From this sprint I started working on the Smart factory detailed design reworked on the estimation.
18061 | Pages to store styling changes | Closed | Raja Dashnamoorthy | 3 | 59
18064 | Clear References / Add to Existing button changes | Closed | Raja Dashnamoorthy | 3 | 59
18065 | Document Viewer Thumbnail Styling Changes | Closed | Raja Dashnamoorthy | 2 | 59
18066 | General control alignment on Documents to Store Page | Closed | Raja Dashnamoorthy | 3 | 59
18067 | References Dynamic Form Changes | Closed | Raja Dashnamoorthy | 3 | 59
18021 | (UX fix) Scroll invalid fields into view | Closed | Raja Dashnamoorthy | 3 | 59
17735 | Speed Development - R&D Vuex store for sticky settings | Closed | Raja Dashnamoorthy | 5 | 59
17949 | Vue3 training (conversion from Vue2 to Vue3) - Raja | Closed | Raja Dashnamoorthy | 1 | 59
17638 | BugFix-Console errors with Error Page | Closed | Raja Dashnamoorthy | 1 | 58 | Oct 5-19 | 1. 7 Story points completed. 2. 3 days leave taken(11, 12,13 and 15) and 2 days holiday. 3. 19 is optional holiday and it is approved but Dinesh havent give leave or comp off for that. I have sacrificed my leave and worked on 19th October. 4. and the Smart factory Came in to picture in this sprint , i have worked on the estimation for smart factory
17644 | Required Reference field on Document to store page is behaving oddly | Closed | Raja Dashnamoorthy | 3 | 58
17636 | Updating lists in store document to support related lists i.e. selection in one list filters the items in another list | Closed | Raja Dashnamoorthy | 3 | 58
17492 | Housekeeping - R&D Exclusion of example modules from production | Closed | Raja Dashnamoorthy | 3 | 57 | Sep17 - Oct 1 | 1. 59 story points completed few of them are carried from the previous sprints. 2. no leave taken
15570 | Create Reindex Control component | Closed | Raja Dashnamoorthy | 30 | 57
15672 | Documents To Store page | Closed | Raja Dashnamoorthy | 18 | 57
17478 | (Bug Fix) List of documents to store does not refresh if there are multiple files uploaded and some fail | Closed | Raja Dashnamoorthy | 3 | 57
17522 | Restrict reference values to configured max or fixed lengths | Closed | Raja Dashnamoorthy | 5 | 57
17232 | Create Thumbnail Store | Closed | Raja Dashnamoorthy | 3 | 56 | Sep 2 - Sep 16 | 1. 33 story points completed few of them are bigger stories and carried out to next Sprint. 2. 2 days leave taken (sep 6 and 7)
15570 | Create Reindex Control component | Closed | Raja Dashnamoorthy | 30 | 56
16103 | Document To Store Api - Re-Index Control - GET | Closed | Raja Dashnamoorthy | 25 | 55 | Aug 16-30 | 1. 25 Story points are completed , few of them are carried over to next sprint 2. 2 days leave taken(aug 20 and 30)
16303 | As a user, I want to drag a file to upload, so I can add new documents for indexing | Closed | Raja Dashnamoorthy | 20 | 54 | July 29 - Aug 12 | 1. 36 story points covered in this sprint 2. no Leave taken
16304 | As a user, I want a progress bar during file upload, so I can see the progress of the upload | Closed | Raja Dashnamoorthy | 8 | 54
16305 | As a user, I want a visual indication of the folder into which a file will be uploaded, so I can see where the file will be stored | Closed | Raja Dashnamoorthy | 5 | 54
16994 | Separate document file and data methods from DocumentService | Closed | Raja Dashnamoorthy | 3 | 54
16722 | As a user, I want to open a job from a Kanban board, so that I can view the document and process the job | Closed | Raja Dashnamoorthy | 2 | 53 | July 13- 27 | 1.21.5 Story points covered in this sprint, 2.user story 16305 is carried forward to the sprint 54, 3. No Leave
16727 | Change validation messages to use validation type toaster rather than report an error | Closed | Raja Dashnamoorthy | 0.5 | 53
16280 | Refactor - Remove workflow dependencies from shared components needed for storing documents | Closed | Raja Dashnamoorthy | 3 | 53
16355 | Refactor workflow to use shared components | Closed | Raja Dashnamoorthy | 13 | 53
16705 | BUG FIX: Unable to move the cards one position up for the cards at position 3rd order positions | Closed | Raja Dashnamoorthy | 3 | 53
16130 | Container screen - top level component to show multiple columns of data | Closed | Raja Dashnamoorthy | 20 | 52 | June 25 - July 9 | 1. 45 Story points completed 2. April 29, 30 and july 1 and 9 I took leave.
16134 | Job Card list sizing behaviour | Closed | Raja Dashnamoorthy | 8 | 52
16137 | Job Card - mouse hover display | Closed | Raja Dashnamoorthy | 3 | 52
16138 | Filtering on the Kanban board | Closed | Raja Dashnamoorthy | 5 | 52
16353 | (R&D) As a user, I want the job form horizontal tabs to pop up, so I can save a click when entering data | Closed | Raja Dashnamoorthy | 3 | 52
16623 | Wall board mode not supports the additional work field popups | Closed | Raja Dashnamoorthy | 3 | 52
16624 | When the user attempts to move a card to an illegal lane, there's no message to inform them it was aborted | Closed | Raja Dashnamoorthy | 3 | 52

## 2-Feb-2022
Sno | Task | Duration (mins) | Time | Date | Total
1 | 18651-HLD - how to detect application updates | 60 | 9-10 am | 2022-02-02 | 8.4667
2 | Helped Boopathy for Sprint review and clarified few doubts on 6422 | 60 | 11-12 pm
3 | Had vpn issue not able connect my RDC | 20 | 12-12.20 pm
4 | Had a call with HR | 15 | 12.30 to 12.45 PM
5 | Had call with Karthik | 48 | 1.48 to 2.37 pm
6 | Sprint Retro | 40 | 2.37 - 3.10 pm
7 | Stand up | 10 | 3:20 -3.30 pm
8 | Call with Andrew | 30 | 3.36pm to 4.06 pm
9 | Call with Boopathy on the Exploratory testing on 6422 | 24 | 4.06 to 4.30 pm
10 | Data points preparation on esclation | 90 | 4.30 to 6 pm
11 | call with Karthik | 6 | 6.09 to 6.15 pm
12 | 18651-HLD - how to detect application updates | 45 | 6.15 to 7 pm
13 | Sprint review | 60 | 7-8 pm
1 | 18651-HLD - how to detect application updates | 120 | 9-11 am | 2022-02-03 | 8.5
2 | Housekeeping - R&D into vue debugging | 150 | 11 am to 1.30 pm
3 | Housekeeping - R&D into vue debugging | 30 | 2:45 pm to3.15 pm
4 | Arena Stand up | 15 | 3.15 pm to 3.30 pm
5 | Housekeeping - R&D into vue debugging | 60 | 3.30 pm to 4.30 pm
6 | Backlog refinement | 30 | 4.30 pm to 5pm
7 | 18651-HLD - how to detect application updates | 30 | 5pm to 5.30 pm
8 | Housekeeping - R&D into vue debugging | 75 | 5.30 to 6.45 pm
1 | Housekeeping - R&D into vue debugging | 360 | 8 am to 3:15 pm | 2022-02-04 | 8.25
2 | Stand up | 15 | 3.15 pm to 3.30 pm
3 | Housekeeping - R&D into vue debugging | 120 | 3.30-5.30 pm
1 | Email check | 15 | 10.30 to 10.45 am | 2022-02-07 | 8.4167
2 | Housekeeping - R&D into vue debugging - Document preparation | 45 | 10.45 to 11.30 am
3 | Implement browser refresh if application update has been detected - development | 30 | 11.30-12pm
4 | Housekeeping - R&D into vue debugging - Document preparation | 30 | 2:45 - 3:15pm
5 | Stand up | 15 | 3.15 pm to 3.30 pm
6 | Implement browser refresh if application update has been detected - development | 330 | 3.30 pm - 9pm
7 | Call with Andrew | 40 | 9-9.40pm
1 | Housekeeping - R&D into vue debugging - Document preparation | 90 | 10-11.30 am | 2022-02-08 | 8.3333
2 | Implement browser refresh if application update has been detected - development | 150 | 11.30-2pm
3 | Implement browser refresh if application update has been detected - development | 15 | 3-3:15pm
4 | Stand up | 15 | 3:15 - 3.30pm
5 | Implement browser refresh if application update has been detected - development-Testing | 230 | 3.30-7.20pm
1 | Implement browser refresh if application update has been detected - development-Testing | 120 | 8.30-10.30 am | 2022-02-09 | 8.5
2 | Implement browser refresh if application update has been detected - development-Testing | 90 | 11-12.30 pm
3 | Implement browser refresh if application update has been detected - development-Testing | 90 | 1pm-2.30pm
4 | Standup | 15 | 3:15-3.30pm
5 | Implement browser refresh if application update has been detected - development-Testing | 120 | 3.30-5.30
5 | Implement browser refresh if application update has been detected - development-Testing | 75 | 6:15 -7.30pm
1 | Implement browser refresh if application update has been detected - development-Testing | 390 | 7.30-2pm | 2022-02-10 | 8.75
2 | Stand-up | 15 | 3.15-3.30pm
3 | Backlog refinement session | 60 | 3.30pm to 4.30 pm
4 | Call with Andrew to discuss | 30 | 6 pm - 6.30 pm
5 | Vue debugging document updation | 30 | 6 pm - 6.30 pm
1 | Implement browser refresh if application update has been detected - development-code review changes | 195 | 11-3pm(1hour lunch) | 2022-02-11 | 8
2 | Stand-up | 15 | 3.15-3.30pm
3 | Implement browser refresh if application update has been detected - development-code review changes | 30 | 3.30pm - 4 pm
4 | User story 18918 | 120 | 4 pm - 6 pm
5 | User story 18918 | 120 | 6.30 pm - 8.30 pm
1 | User story 18918 | 60 | 8-9am | 2022-02-14 | 8.9167
2 | User story 18891 | 300 | 9-2am
3 | Stand-up | 20 | 3.15-3.35pm
4 | User story | 30 | 3.35-4.05pm
5 | User story 18891 | 125 | 4.05-6.10pm
1 | Code review -19133 | 120 | 8-10am | 2022-02-15 | 9
2 | User story 18891 | 195 | 11-2.15pm
3 | Stand-up | 15 | 3.15-3.30pm
4 | Code review -19133 | 30 | 3.30-4pm
5 | User story 18891 | 150 | 4-5.30pm
6 | Backlog refinement | 30 | 5.30-6pm
1 | User story 18891 | 120 | 8-10am | 2022-02-16 | 8.75
2 | User story 18918-bug fix | 120 | 11-1pm
3 | Stand-up | 15 | 3.15-3.30pm
4 | Code review -19133 | 30 | 3.30-4pm
5 | User story 18891 | 150 | 4-5.30pm
6 | User story 18652 | 30 | 5.30-6pm
7 | User story 18891 | 60 | 6.30-7.30pm
1 | User story 18891 | 300 | 9-2pm | 2022-02-17 | 9.25
2 | Stand-up | 15 | 3.15-3.30pm
3 | User story 18891 | 60 | 3.30-4.30pm
4 | Backlog refinement | 60 | 4.30-5.30pm
5 | User story 18891 | 60 | 5.30-6.30pm
6 | Sprint review | 60 | 7.30-8.30pm
1 | User story 18891 | 360 | 8-2pm | 2022-02-18 | 8.5
2 | Retro | 60 | 2.30-3.30pm
3 | User story 18380 | 60 | 4.30-5.30pm
4 | Sprint planning | 30 | 7.30-8pm
1 | User story 18380 | 240 | 10-2pm | 2022-02-21 | 8.25
2 | Stand-up | 15 | 3:15-3.30pm
3 | User story 18380 | 240 | 3.30-7.30pm
1 | Sowmiya developer test review | 90 | 5.30-7am | 2022-02-22 | 8.25
2 | KT document preparation | 90 | 9-10.30am
3 | User story 18891 | 120 | 10.30-12.30pm
4 | Stand-up | 15 | 3.15-3.30pm
5 | backlog refinement | 30 | 3.30 -4pm
6 | Call with Andrew | 30 | 4.30-5pm
7 | User story 18891 | 90 | 5-6pm
4 | Call with Sowmiya | 30 | 6.60-7pm
1 | User story 18891 | 360 | 10-1pm | 2022-02-23 | 9.25
2 | KT-Sowmiya | 60 | 1-2pm
3 | Stand up | 15 | 3-3.15pm
4 | User story 18891 | 120 | 5-7pm
1 | User story 6422 bug fix | 255 | 10-2:15pm | 2022-02-24 | 8.25
2 | Stand up | 15 | 3.15-3.30pm
3 | Backlog refinement | 30 | 3.30-4pm
4 | User story 6422 bug fix | 195 | 4-7.15pm
1 | User story 18891 |  | 10.30- | 2022-02-25 | 0
2 | User story 6422 bug fix
3 | User story 18380
4

## Sheet2
S.No | Topic | Owner | Date | Timing
1 | Overall Architecture-Authentication | Raja | 2022-02-22 | 11.30 to 12pm
2 | Mstore V5-Api | Raja | 2022-02-23 | 11.30 to 12pm
3 | MStore V5-UI | Raja | 2022-02-24 | 11.30 to 12pm
4 | Mstore V5-Configurations and database tables | Boopathy
5 | Mstore V3 | Boopathy
6 | Mstore V4 | Boopathy